## Sheet1
Epic ID | Epic | Priority | Story ID | Story Title | Description | Acceptance Criteria | API/Backend | UI/Frontend | Tests | Status | Estimate (pts) | Owner | Depends On
E15 | Router decision trace + Policy Explain | P0 | E15-S1 | Policy Explain (full trace) on Node Inspector | Expand Router Decision to show allow/deny chain, rule path, and inputs. | Click 'Explain' shows rule path, matched conditions, and final decision. | POST /policies/explain (extended fields: rulePath, inputs); GET /runs/:id/nodes/:nodeId/routing | Node Inspector → 'Explain' drawer with trace. | ui snapshot; contract test for rulePath & inputs. | Ready | 3 |  | E6-S1
E15 | Router decision trace + Policy Explain | P0 | E15-S2 | What-if policy simulator (node scope) | Simulate proposed changes to policy for a node and preview impact. | Given inputs + rule, returns hypothetical decision & deltas. | POST /policies/simulate | Explain drawer → What-if tab returns decision deltas. | e2e simulate happy/deny; unit rule delta format. | Ready | 5 |  | E15-S1
E16 | Serving lane trends | P0 | E16-S1 | Add trend charts for qDepth/batch/KV hit | Render per-metric mini line charts (no style deps) and show p95 latencies. | Charts render valid series from /serving/metrics. | GET /api/maestro/v1/serving/metrics (series) | Observability → Serving Lane panel charts. | ui smoke; timeseries unit mapping. | Ready | 3 |  | E11-S1
E16 | Serving lane trends | P0 | E16-S2 | Drill-down view per backend (vLLM/Ray/Triton/KServe) | Backend switcher with metric breakdown and last-30m detail. | Switcher filters data; detail table paginates spans. | GET /serving/metrics?backend=...; GET /serving/spans?backend=... | Observability → detail drawer. | e2e switcher; contract: backend filter respected. | Ready | 3 |  | E16-S1
E17 | Evidence export | P0 | E17-S1 | Export Evidence (JSON + signed bundle) | Click 'Export' produces JSON + signature bundle including SBOM/Cosign/SLSA. | Download works; verify via /provenance/verify. | POST /evidence/export; POST /provenance/verify | Evidence tab → Export button; Verify action. | e2e export→verify roundtrip. | Ready | 5 |  | E13-S1
E17 | Evidence export | P0 | E17-S2 | Artifact links (SBOM, attestation) | Badge links open artifact detail; copy URIs. | Link resolves; copy-to-clipboard works. | Artifacts served at /artifacts/:id | Evidence tab: artifact drawer. | ui snapshot; 404 case. | Ready | 2 |  | E17-S1
E18 | Build health | P0 | E18-S1 | Type through non-Maestro src/App.tsx | Fix types, remove @ts-nocheck, add strict settings for Maestro build. | CI passes 'build' and 'build:maestro'. | — | — (TS fixes in repo) | CI job green; unit compile step. | Ready | 5
E18 | Build health | P0 | E18-S2 | tsconfig split + path aliases | Introduce tsconfig.maestro.json and base tsconfig for monorepo. | Both builds share base; Maestro has strict flags. | — | — | CI matrix builds; lints pass. | Ready | 3 |  | E18-S1
E19 | AlertCenter correlation | P1 | E19-S1 | Correlation graph (CI failures ↔ SLO burn ↔ cost anomalies) | Compute correlations in window and surface likely related events with confidence score. | Correlated cluster contains ≥2 event types; score displayed. | GET /alertcenter/correlate?sinceMs=... | AlertCenter → clusters list with detail drawer. | unit: scoring fn; e2e: cluster renders. | Ready | 5
E19 | AlertCenter correlation | P1 | E19-S2 | Rule engine + mute/snooze | Admin can define correlation rules and mute/snooze routes. | Rules persist and apply to correlation view; snooze hides non-actionables. | POST/GET /alertcenter/rules; PUT /alertcenter/mutes | AlertCenter → Rules tab; snooze control. | e2e: rule modifies clusters; mute hides alerts. | Ready | 3 |  | E19-S1
E20 | Agent/HITL | P1 | E20-S1 | Show Planner/Critic/Executor with HITL checkpoints | Timeline shows agent roles; HITL steps marked with decisions. | Steps render with metadata from run graph. | GET /runs/:id/agents/timeline | Run Detail → 'Agent Timeline' tab. | ui smoke; contract tests for roles. | Ready | 5
E20 | Agent/HITL | P1 | E20-S2 | Approve/Edit/Block HITL actions | Operators can approve/edit/block at checkpoints; result applied to run. | Server records decision; run state updates. | POST /runs/:id/hitl/:checkpoint/{approve¦edit¦block} | Action bar with shortcuts & keyboard handlers. | e2e: block halts; approve resumes; edit mutates input. | Ready | 5 |  | E20-S1
E21 | CICD upgrades | P1 | E21-S1 | Annotations by env/branch + filters | Render GH annotations filtered by env/branch; quick filters. | Filter state preserved in URL; deep links persist. | GET /ci/annotations?env=&branch= | CICD page updated; filters & saved state. | ui test: filter chips; contract: query respected. | Ready | 3
E21 | CICD upgrades | P1 | E21-S2 | Flake detector & test stability stats | Compute test flakiness and show stability trend per test. | Trend chart renders; flake rate per test shown. | GET /ci/tests/flakiness?sinceMs=... | CICD → 'Flakes' tab with table + trend. | unit: flake scoring; ui smoke. | Ready | 5 |  | E21-S1
E22 | A11y sweep | P1 | E22-S1 | Integrate axe-core CI + local ‘a11y:check’ | Add accessibility checks to CI; fail on serious violations. | CI fails on critical issues; report artifact uploaded. | — (dev deps + scripts) | — (jest-axe for component tests) | CI artifact contains axe report. | Ready | 3
E22 | A11y sweep | P1 | E22-S2 | Live regions & focus order audit | Streaming logs and alerts announce changes; dialogs have aria-describedby. | Screen readers announce updates; focus order validated. | — | Apply to Command Palette, Replay dialog, AlertCenter. | manual a11y checklist; unit for live region hooks. | Ready | 3 |  | E22-S1